## Excel Gantt Chart
APCRSHR Tasks Estimation
APCRSHR |  |  | PERSON IN CHARGE | STATUS | PERCENT COMPLETED | COMMENT | DURATION (days)
START DATE | END DATE | DESCRIPTION | [5 empty] | GHI CHÚ:
2016-02-18 | 2016-02-21 | Trang Chủ | Đoàn | n/a | 20% |  | 3
2016-02-18 | 2016-02-22 | Article | Đoàn | n/a | 90% |  | 4
2016-02-18 | 2016-02-19 | Important Deadline | Trang | n/a | 0% |  | 1
2016-02-20 | 2016-02-21 | Slider | Trang | n/a | 0% |  | 0